## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 |  | Project Introduction & Problem Understanding | MUST HAVE | No Dependency | PRADEEP | COMPLETED | Completed
S1 | S1 |  | Data Source Identification (Social Media, Reviews, News) | MUST HAVE | APIs, Public Datasets | PRADEEP | COMPLETED | In Progress
S2 | S2 |  | Data Collection & Scraping Setup | MUST HAVE | Scrapy, Social Media APIs | PRADEEP | COMPLETED
S2 | S2 |  | Data Cleaning & Normalization Pipeline | MUST HAVE | Python, Pandas | PRADEEP | COMPLETED
S2 | S2 |  | Unified Data Schema Design (final columns) | MUST HAVE | cleaned data | PRADEEP | COMPLETED
S3 | S3 |  | Sentiment Analysis Implementation | MUST HAVE | (Rule-based / VADER)/ BERT | PRADEEP | COMPLETED
S4 | S4 |  | Topic Modeling for Trend Extraction | MUST HAVE | BERTopic / LDA | PRADEEP | COMPLETED
S5 | S5 |  | Dashboard Wireframe & UX Planning | SHOULD HAVE | Design overview | PRADEEP | COMPLETED
S5 | S5 |  | Sentiment & Trend Visualization Dashboard | MUST HAVE | Plotly and Streamlit | PRADEEP | COMPLETED
S6 | S6 |  | RAG Pipeline Design & Integration | MUST HAVE | Python/LangChain | PRADEEP | COMPLETED
S7 | S7 |  | Vector Database Setup | MUST HAVE | Pinecone | PRADEEP | COMPLETED
S8 | S8 |  | Contextual Consumer Insight Generation | MUST HAVE | RAG Pipeline | PRADEEP | COMPLETED
S9 | S9 |  | Alert System for Sentiment Spikes | MUST HAVE | Python, Scheduler | PRADEEP | COMPLETED
S10 | S10 |  | Automated Report Generation (PDF/Excel) | MUST HAVE | Pandas | PRADEEP | COMPLETED
S11 | S11 |  | Project Documentation & Demo Preparation | MUST HAVE | README, PPT | PRADEEP | COMPLETED

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7